## Product Backlog
Product Backlog
ID | Name | Imp | Est | How to Demo | Notes | Track | Component | Requestor | Bug Tracking ID
1 | Load list |  |  | Display a list of available loads for everyone to see De lijst heeft de volgende indeling : Posted From To Load type Weight Arrive after Arrive before Taken 10-04-2010 Lusaka Ndola steel pipes 60 ton 10-04-2010 20-04-2010 No/Yes/Cancelled As default the data is ordered the columns by posted date, most recent up. User can change the order by clicking on the headers: posted, from, to , arrive after, arrive before, taken. A transporter logged into the system can click on any of the loads to see the details. Only the customer who posted the load can modify the load, He can cancel the load, indicate the load is taken or update the load. This can also be done through the three URL’s send to the transporter when posting a load. A customer logged into the system will see only his loads, and an additional button show all loads. Admin parameter: number of loads displayed by page Issues: |  | Webapplication

## Sprint backlog week
Sprint backlog week 14 march
ID | Name | Imp | Est | How to Demo | Notes | Track | Progress
1 | F2 : Show load list | 100 | 20 | Display a list of available loads for everyone to see.: Posted From To Load type Weight Arrive after Arrive before Taken 10-04-2010 Lusaka Ndola steel pipes 60 ton 10-04-2010 20-04-2010 No/Yes/Cancelled As default the data is ordered the columns by posted date, most recent up. User can change the order by clicking on the headers: posted, from, to , arrive after, arrive before, taken. |  |  | wip
| F2: Show load | 100 | 20 | Only the customer who posted the load can modify the load, He can cancel the load, indicate the load is taken or update the load. This can also be done through the three URL’s send to the transporter when posting a load.
| F2 : Edit load detail | 50 | 40 | A customer and transporter can log in to the system.
| F2: Show personal load | 70 | 20 | A customer logged into the system will see only his loads, and an additional button show all loads.
| F2: Register user | 50 | 70 | A user can register as a customer or a a transporter The adminstrator has to approve the user to log in.
| F2 : Make login | 70 | 50 | Make a login system for user. There are to type of users : customer en transporter. Both see different starting pages.
| F2: Edit/Show Customer detail | 70 | 50 | After logging in the customer will see his personal page with detail information
| F2: Edit/Show Transporter detail | 70 | 50 | After logging in the transporter will see his personal page with detail information